Evaluation of Implementation of NREGS in Orissa

Social Audit Report

Centre for Planning, Monitoring & Evaluation

National Institute of Rural Development, Hyderabad

August 2008

CONTENTS

| Sl. No. | Topic | Page Nos. |
| --- | --- | --- |
|  | Contents | ii |
|  | List of Tables | iii |
|  | List of Annexures | iv |
|  | Acknowledgement | v |
| 1. | Introduction | 1 |
| 2. | Objectives | 1 |
| 3. | Sample for Social Audit | 2 |
| 4. | Social Audit Process | 2 |
| 5. | Limitations of study | 3 |
| 6. | Period of the study | 4 |
| 7. | Finding of Social Audit | 5-19 |
| 8. | Major Conclusions | 20 - 22 |
|  | Annexures | 23-36 |

LIST OF TABLES

| Sl. No. | Topic |
| --- | --- |
| Table 1 | Sample for Social audit |
| Table 2 | Registration and Issue of Job-card |
| Table 3 | Muster Roll Discrepancies – 1 (% Actual no. of beneficiaries v/s reported beneficiaries |
| Table 4 | Muster Roll Discrepancies – 2 (% Actual no. of man days v/s reported man days |
| Table 5 | Muster Roll Discrepancies – 3 (% Actual wages received v/s reported wages paid |
| Table 6 | Discrepancies by PIAs |
| Table 7 | Region-wise discrepancies |
| Table 8 | Significant Improvement in NREGS implementation in 2007-08 |

LIST OF ANNEXURES

| Sl. No. | Topic |
| --- | --- |
| Annexure - 1 | District wise Implementing Agency of Audited Works |
| Annexure - 2 | District Wise year of Implementation of Audited Works |
| Annexure - 3 | District Wise Status of Audited Works |
| Annexure - 4 | Social Audit Details/ Volunteers |
| Annexure - 5 | Household Enumeration on NREGS Registration Details |
| Annexure - 6 | Household Enumeration on NREGS Job Card Details |
| Annexure - 7 | Number of Reported and Actual Beneficiaries |
| Annexure - 8 | GP Wise reported and Actual Beneficiaries |
| Annexure - 9 | GP Wise Reported and Actual Person Days |
| Annexure - 10 | GP Wise Reported and Actual Wage Payment |

ACKNOWLEDGEMENT

It is a matter of great privilege that the Govt. of Orissa has chosen NIRD to take up evaluation of the implementation of NREGS in the state.  The Chief Secretary himself took keen interest to ensure that an independent and objective evaluation is done and accordingly given instructions to all concerned to cooperate with the evaluation team of NIRD.  Shri R N Dash, Principal Secretary, Shri Baider Biswal, Addl. Secretary and  more particularly Shri Saswat Mishra, Director (Spl. Projects) of Panchayat Raj Department extended whole hearted support and cooperation for the successful conduct of the Social Audit in 40 Gram Panchayats spread over 19 Phase-I districts. The District Collectors, Project Directors of DRDAs, Block Development Officers, Sarpanches, Panchayat Extension Officers and others provided the needed information and support.

The whole exercise was possible because of the dedicated leadership of Shri Raj Kishore Mishra of RUPAYAN and his committed team.  More than 25 NGOs took the responsibility for 40 Social Audits and nearly 400 volunteers from NGO groups across the state sweated it out to conduct the Social Audit.  The workers particularly women participated in large scale in the social audit to make it fully a people’s exercise.  SIRD has assisted in the training of the volunteers and also hosted the Social Audit Findings Sharing Workshop.

There were several others who worked behind the scene to carryout this audit and also document the processes.  I wish to thank all those directly and indirectly helped us in this evaluation.

Dr S. Rajakutty

Project Director

1.  Introduction

National Rural Employment Guarantee Scheme (NREGS) was launched in February 2005 to cover 200 districts in the country.  In the second year, the scheme was extended to additional 150 districts.  Since April 2008, the scheme stands extended to cover all the districts in the country.  The NREGS is hailed as an historic achievement and therefore has attracted wide attention across the country and across a cross sections of society, particularly, the activists, NGOs, Civil society organization, academics, development worker/ thinkers etc.   Certain provisions like Social Audit and Right to Information have enabled Civil Society sponsored scrutiny & monitoring of the implementation of the scheme across the states.  Many such initiatives have brought to light several short comings/ discrepancies/ irregularities in the implementation of the scheme which primarily indicate that benefits are not reaching the intended beneficiaries, the guarantee component is missing and planning has been inadequate to provide succour to the poor.  Orissa is one of the states which has been the focus of academics, media and others alike.  In the light of this, the Government of Orissa requested National Institute of Rural Development (NIRD) to carry out an independent concurrent evaluation of the implementation of the NREGS in Orissa and provide necessary feed back to effect appropriate corrective measures and put the scheme on right course.  The evaluation comprised two parts; one, personal interview of 1600 workers (job card holders who worked in the scheme) and 400 non workers (job card holders but not worked) and a Social Audit.   This report is based on the social audit; the social audit reports of 40 GPs have already been submitted to Government of Orissa.

2. Objectives

Keeping the above in the backdrop, the objectives of the study were set as below:

  - Analyze the performance of implementation of NREGS

  - Assess people’s awareness and participation level

  - Study and evaluate the planning process and implementation arrangement including aspects of transparency

  - Assess the benefits that accrued to workers under NREGS

- Analyze the type of works taken up vis-à-vis guidelines

- Carryout social audits to assess the ground realities and people’s perception on the outcomes of the schemes

- To study the level of preparedness in the new 5 districts and the extent of incorporation of the lessons learnt from the earlier districts.

3.  Sample for Social Audit

The study was restricted to the 19 districts of Phase – I of NREGS.  A total of 40 blocks from the 19 districts were selected based on the highest physical and financial performance.  In each block the Gram Panchayat (GP) that posted the highest physical and financial achievements was selected.  Incidentally, most of these GPs turned out to be interior GPs.  The full details of sample can be seen in Table -1.  (See also Annexures 1-3 for more details of PIAs, year of work, number of works audited)

4.  Social Audit Process

All NGOs who were doing some social audit and those who were trained under an earlier project of NIRD to build capacities for Social Audit were contacted from the districts in Orissa.  Twelve NGOs and 40 trained volunteers were available through this search.  RUPAYAN, an NGO was designated as the lead NGO to coordinate the networking and identify other NGOs who were willing to take up social audit.  This wide ranging consultation indicated that this social audit process should also be utilized to build capacities among more NGOs and activists.   Accordingly, in collaboration with SIRD, Bhubaneswar, a five day training programme was organized with 3 days orientation to social audit concepts and two days field exposure.   After this, one or two NGOs were designated as lead NGO for a district and 6-10 member team was formed for each GP selected for Social audit.  In each team 2-3 previously experienced volunteers were included.  In each GP, 5-6 days of social audit exercise was planned.  The activities included collection of data from block & GP, compilation and consolidation, field verification of works/ workers, preparation of report, culminating in a public hearing.  In addition, complete household enumeration was also taken in these GPs to ascertain/ identify the households, registered, not registered, issued with job cards, worked with scheme,  want to work in the scheme etc. (See Annexure – 4 for participating NGOs)

5.  Limitations of study

B.   The sample GP for Social Audit was kept secret till a couple of days before the initiation of Social Audit and the needed records and documents were procured/ obtained as per instructions from government in a short period thereby giving less scope to ‘adjust’ or ‘make-up’ the records.  Nevertheless, in many villages the Social Audit teams faced the following problems.

- The records/ registers/ documents were not provided by the concerned officials till last date of social audit process leaving little time for verification

- The line departments brought the registers/ documents only on the day of public hearing and thereby making the Social Audit ineffective

- The elected representatives, labour leaders, un-official contractors disrupted the public hearing in many places.  In fact, the officials and contractors have threatened or enticed the workers the night before the public hearing so as to not to talk or provide testimony in the public hearing

- Some instances of physical assault of whistle blowers and those offered testimonies (both men and women) have unnerved people in other villages to come out openly

- Recall/ memory bias of workers in giving correct details of the number of days of work and wages received.

In addition to the above, there were some shortcomings on the part of the Social Audit Team.   The members were newly trained, and over-enthusiastic at times and therefore the Social Audit process in some places did not follow the desired standards.  Besides, the over-exposure of the scheme both positively and more negatively in the media has made the SA and evaluation a very sensitive exercise.  In order to overcome these limitations, efforts were made through a ‘triangulation’ process to arrive at reasonably reliable assessment of status of implementation of NREGS in Orissa.

6.  Period of the Study

The Social Audit was done in four phases starting from Februry and completing it by the 10 June 2008.  Since the Social Audit had a wide coverage, finding suitable persons, training them and organizing them into teams took quite a bit of time than anticipated.  It was intended to form teams from within the block/ district so as to leave behind a capacity in every district. This was a time consuming process.

Table – 1 :   Sample for Social audit

| Sl.No. | District | Block | GP |
| --- | --- | --- | --- |
| 1. | Bolangir | Agalpur | Duduka |
|  |  | Belpara | Gambhari |
|  |  | Titlagarh | Bijepur |
| 2. | Boudh | Kantamal | Similipadar |
| 3. | Deogarh | Barkote | Saruali |
| 4. | Dhenkanal | Hindol | Baunsa Pokhari |
|  |  | Kankadahad | Kantapal |
| 5. | Gajapati | Kasinagar | Siali |
|  |  | Mohona | Chandiput |
| 6. | Ganjam | Kukudakhandi | Sihala |
|  |  | Surada | Asurabandha |
|  |  | Sheragada | Mahupadar |
| 7. | Jharsuguda | Lakhanpur | Panchagaon |
| 8. | Kalahandi | Bhawanipatna | Artal |
|  |  | Karlamunda | Joradobra |
| 9. | Kandhamal | Phiringia | Luisingi |
|  |  | Tikabali | Gutingia |
| 10. | Kendujhar | Ghatgaon | Sarasa Pasi |
|  |  | Kendujhar Sadar | Raikala |
|  |  | Saharapada | Malarpada |
| 11. | Koraput | Borigumma | Pondasguda |
|  |  | Nandapur | Khurji |
|  |  | Bandhugaon | Nilabadi |
| 12. | Malkangiri | Korukonda | Nuaguda |
|  |  | Malkangiri | Gangala |
| 13. | Mayurbhanj | Gopabandhunagar | Arapata |
|  |  | Badasahi | Chandanpur |
|  |  | Saraskana | Murunia |
|  |  | Rasgovindpur | Debasole |
| 14. | Nabarangapur | Papadahandi | Papadahandi |
|  |  | Chandahandi | Gambariguda |
| 15. | Nuapada | Sinapali | Ghatamal |
| 16. | Rayagada | Rayagada | Gumma |
|  |  | Chandrapur | Piskapanga |
| 17. | Sambalpur | Kuchinda | Hadipali |
|  |  | Rairakhol | Badbahal |
| 18. | Subarnapur | Biramaharajpur | Mursundhi |
| 19. | Sundargarh | Bargaon | Ekma |
|  |  | Kutra | Ambhagova |
|  |  | Bonaigarh | S.Balang |

7.  Finding of Social Audit

7.1  Positive signals on NREGS Implementation

The NREGS implementation during 2006-07, the first year of the scheme, faced several teething problem and studies by various agencies and organizations pointed out several shortcomings and deficiencies in implementation.  It is natural to expect such inadequacies when a ‘change process’ was expected in the way a scheme is planned and implemented.  The NREGS had upset several vested interests who benefited at the cost of intended  beneficiaries.  The vested interests included officials, non officials, contractors etc. who got used to a ‘system’ which was being dismantled and were resisting the change and continued with old practices.  The ‘percentage system’ of making cuts in each work was a ‘lubricant’ which kept the vested interest happy and satisfied.  During the period, with the orientation, sensitization and followup by state and district administration on the failings that surfaced/ identified have resulted in improved implementation.  The ‘positive signals’ that had come up and noticed during the social audit are listed below:

i.  Projects under NREGS

The number of works taken up in 2006-07 was 58200 and 65468 in 2007-08.  Various studies noted that there were considerable leakage in funds and thereby implying that works were either not carried out or part works were shown as completed.  The social audit has shown that close to 95% of the projects reported under NREGS are true and are either completed or in progress.

ii.  Equity in wages

For the first time in the history, equal wages for men and women has became a reality in most of the districts, barring a few exceptions.

iii.  Awareness on NREGS

Thanks to Social Audit process, publicity campaign etc.  there is a widespread awareness on NREGS with reference to i) 100 days of guaranteed employment, ii) piece rate work – out turn based wages and iii) minimum wages

iv)  Improved staff position

Severe staff shortage and inadequate orientation and training to existing staff was a major constraint in 2006-08.  The initiative of the government to appoint Gram Rojgar Sevak and Gaon Saathi is a boon and eased the constraints to a large extent.  Adequate orientation and training, however, is needed for them.

v)  Improved Maintenance of Records

In the initial year, records/ registers were supplied late and most of the available staff were not fully trained with the new documents.  Staff shortage at GP level added to the problem.  In 2007-08 considerable improvement was seen in the maintenance of records in quite a few GPs

vi)  Transparency Measures

It was quite refreshing to see that the details of NREGS related information displayed as wall writings in most GPs.  Exemplary cases of display was seen in a few GPs.  Though there were some information gaps in the display in many GPs, information of entitlement and rights were clear in most GPs.

vii)  Welcome Response to Social Audit

It is an opt repeated statement across the state that the attendance in the Palli or Gram Sabha is poor.  But, the public hearing Gram Sabhas in the sample villages witnessed a huge participation ranging from 200 – 500 people with substantial women participation.  The faith of people in such Social Audit based gram sabha is quite high and there was a request in almost all the GPs that such meetings should be held frequently.  In fact, there is a demand that the social audit should cover more schemes like PDS, IAY etc.

viii) Improved Village Economy

Thanks to the increased employment opportunities, higher wages and equal wages for women, the spending in the villages is high thereby giving a boost to rural economy.  This is quite visible in those GPs where the programme was implemented fairly well.

ix)  Accountability

The Social Audit processes forced the grass roots officials to face the ire of the people and the contractors also  seen the fury.  They were made to answer or give assurances for their omissions and commissions.  This message has spread across the blocks by word of mouth and also by the media coverage.  There is an ‘accountability fear’ clearly visible among all the concerned.

x)  Best Practices

Works have been assigned to SHGs in some blocks/ GPS.  In such cases it was found that discrepancies were few and execution was of high quality.  It was very heartening to note that in the GPs with women Sarpanches, the transparency measures were exemplary.

xi)  Neglected Areas Receiving Attention

NREGS has reached remotest areas in many blocks.  In fact, there were jubilant response from many such remote and interior villages where development efforts eluded them for decades.  The feeling of neglect has been erased, to an extent, by the implementation of NREGS

7.2  Registration and Issue of job cards

In order check if all the households in a village were given a chance to get registered under the scheme a complete household enumeration was done in the 40 sample GPs.  The information thus obtained was verified with official records.  Information of total number of households, the registration and issue of job cards was available only for 31 GPs and according to that figures nearly 82% of households have registered under NREGS.  The household enumeration of 37715 households showed that only around 62% have registered and 55 percent of these households received the job card.  However, more than 89% of those registered households received the job cards (Table – 2).  Not having BPL ID number was cited to be a reason for this gap.  Nevertheless almost all those families who want to register under NREGS (left out households) wanted to get work under NREGS. (See Annexure – 5 & 6)

Table 2 : Registration and Issue of Job-card

| Sl.No. | Particulars | Data |
| --- | --- | --- |
| 1. | No of GPs where info. available: | 31 |
| 2. | House hold registered as per GP: | 81.77% |
| 3. | No of households surveyed (40 GP): | 37715 |
| 4. | Percentage of HHs registered: | 62.15 |
| 5. | Surveyed HHs having Job-card: | 55.41% |
| 6. | Registered HHs having job card: | 89.16% |

7.3  Major shortcomings in Implementation

i.  Documentation and updating of Records

While non availability of records and registers at the GP is one lapse, these were kept by Panchayat Extension officer or somebody else.  When available, the information was not up-to-date.  Incomplete entries, entry mismatch, no entries etc. are some common shortcomings.  Asset Register was not found in most GPs. Another important document that was invariably absent was job demand register.  Application forms for work or registration were also not available in most GPs.  In  quite a few cases, the job cards were with the PO, PEO, Rojgar sevak or mostly with Village Labour Leader. Several instances of job cards not having numbers, date of issue, photo of the workers signature and seal of issuing officer  etc. were also noticed.

ii.   Registration and Application for work

While GP records indicate that around 82 percent of households have registered for job card, in some villages 85% of households have not registered themselves.  Lack of awareness was found to be the reason.  There are instances of job cards not issued even after two years of registration.  The families not having BPL ID number was the stumbling block.  Though the government had since clarified the position, things have not improved.  The workers are not aware that they have to apply for work.  For those who knew and wanted to apply, the GP offices are not open every day to get themselves registered.  When application was given, the receipt was not issued without which no worker can legally demand compensation.  Usually, when a work is taken up the Sarpanch,  VLL or PEO or GRS calls people to come and work.  In this process, many got missed out.

iii.  Job cards

As mentioned earlier, there were quite a few interested households who did not get job cards.  There were instances of money being demanded for photographs and issue of job cards.  The entries on the job cards were either incomplete or inflated or did not have any entry.  Some job cards had more than 100 days of employment entered.  The job cards were with officials / VLL.  Many of the job cards did not have the number or signatures of issuing officials.  Having a job card did not ensure employment to many families.

iv)  NREGS work plan

The work plan available in GPs contained only a list of works with estimated budget.  Works were decided and taken up as per the decision of Sarpanch/ VLL/ engineers etc. and palli or Gram Sabha decisions were handling a part of the work plan.  There was delay in approval and allotment of works by DPC, thereby workers were denied opportunity to earn wages.

v)  Ineligible works

Works like CC road and buildings which were not permitted and also work that involve high proportion of materials were taken up in many GPs.  Oral instructions to carry out some un-approved works but shown as some other works were also noticed in some districts.

vi)  Discrepancies in Muster Roll

Muster roll is among the most important document under NREGS.  In fact, several studies pointed out widespread discrepancies in the muster roll and alleged misappropriation.  In the light of this, the social audit devoted considerable attention to verify the real situation in the sample GPs.   The findings have been analysed under the following three broad indicators.

- Actual number of beneficiaries of the scheme against the reported/ recorded number of beneficiaries.

- Actual number of man days worked by the beneficiaries against the reported/ recorded number of man days

- Actual wages realized by the beneficiaries against the reported/ repayment of wages

Caution: The data presented here include the verbal statement of workers. They had difficulty in recalling the exact number of days of their employment and wages received. It is, therefore, necessary to read this finding giving allowance to recall/memory bias of the workers.

a)  Actual Number of Beneficiaries

In the works that were chosen for social audit in the 40 GPs, the records (muster roll) showed involvement of 12037 workers.  Around 53 percent of these workers (6381) could be contacted and only 4380 or 69 percent confirmed having worked.   In other words, close to a third of the workers (31%) seemed to be ghost workers.   While no such discrepancies were noticed in Ganjam and Naupada disricts, Kalahandi fared very badly in this regard (Table 3) followed by Dhenkanal, Malkangiri and Sambalpur.  Inflated muster roll is evident. (See also Annexures 7 & 8)

Table – 3:  Muster Roll Discrepancies – 1

Percentage of Actual No. of beneficiaries v/s reported beneficiaries

| Range | Districts |
| --- | --- |
| 100 % | Ganjam(100), Nuapada (100) |
| 76 – 100 % | Bolangir (85), Jharsuguda (98), Kandhamal (94), Sundergarh (82), Mayurbhanj (85) |
| 51 – 75 % | Boudh (71), Deogarh (70), Gajapati (73), Kendujhar (71), Koraput (72), Rayagada (56), Nawarangpur (69) |
| 26 – 50 % | Dhenkanal (41), Malkangiri (30), Sambalpur (30) |
| 25 % and below | Kalahandi (24) |

Total beneficiaries = 12037

Sample beneficiaries = 6381

Actual beneficiaries from sample = 4380

Over all % = 68.64

Findings: close to 32% workers are ghosts !!!

b)  Actual number of mandays

While the number of ghost workers was found to be around 31 percent, the actual number of days of work was less than half of what has been shown in muster roll.  For the sample workers (6381), the reported number of mandays was 1,15,345 while the verification with workers indicated only 54,860 mandays (47.6%).   In other words, around 53 percent of the reported mandays appeared to be ghost mandays.   Malkangiri also joined in this second stage of evaluation among the worst performers (Table -4).  It is dishealening to note that all the KBK districts showed very significant divergence. (See also Annexure – 9)

Table – 4:  Muster Roll Discrepancies – 2

Percentage of Actual No. of man days v/s reported man days

| Range | Districts |
| --- | --- |
| 100 % | Ganjam (100) |
| 76 – 100 % | Kandhamal (87), Mayurbhanj (77) |
| 51 – 75 % | Boudh (55), Gajapati (70), Jharsuguda (60), Rayagada (54), Sundergarh (56) |
| 26 – 50 % | Bolangir (47), Deogarh (29), Dhenkanal (27), Kendujhar (28), Koraput (49), Nawarngpur (35), Nuapada (36), Sambalpur (39) |
| 25 % and below | Kalahandi (12), Malkangiri (16) |

Total man days = 228038

Sample recorded man days = 115345

Actual man days = 54860

Over all percentage = 47.56

Findings: Close to 53% man days are ghost !!!

c)  Actual Wages  Received

This indicator showed more disturbing outcomes.  Against the reported muster roll payment of Rs.81,04,896 for the sample workers, the amount actually paid worked out to Rs.33,88,795 which was only 42 percent of the wages reported in muster roll.  In other words,  58 percent of the reported payment did not reach the workers (Table 5).  Among the districts, Ganjam and Kandhamal showed the least divergence.  The number of districts showing the worst or large scale divergences rose to six under this indicator.  It is a matter of concern that all the KBK districts which are the poorest and backward districts in the state showed worst record of performance. (See also Annexure 10)

Table – 5:  Muster Roll Discrepancies – 3

(% Actual wages received v/s reported wages paid)

| Range | Districts |
| --- | --- |
| 100 % | Nil |
| 76 – 100 % | Ganjam (98), Kandhamal (88) |
| 51 – 75 % | Gajapati (52), Jharsuguda (66), Sundergarh (54), Mayurbhanj (72) |
| 26 – 50 % | Bolangir (43), Boudh (47), Deogarh (34), Nawarangpur (27), Nuapada (41), Rayagada (47) |
| 25 % and below | Dhenkanal (25), Kalahandi (12), Kendujhar (25), Koraput (25), Malkangiri (11), Sambalpur (43) |

Total wages paid to sample beneficiaries as per record = Rs. 8104896/-

Actual wages received by beneficiaries Rs.3388795/-

Over all percentage = 41.81

Findings: More than 58% of the reported wage payments are bogus

d)  Discrepancies by Implementing Agencies

Generally, GPs, Panchayat Samities and Line Departments are the implementing agencies under NREGS.  Since the details of works allotted to line departments were not available with the PO or GPs, only one work could be checked under the social audit.  The actual wages reaching the workers was relatively better under PRIs with Panchayat Samities showing marginally better performance at 45 percent against the 42 percent by GPs (Table – 6).  The line departments exhibited worst performance at 22 percent.  Wide spread use of machineries and showing them against worker wages was reported to be one of the reasons.  Another reason was engagement of workers under spill over works of SGRY at old wage rates but posting them under NREGS wage rate.  In any case, considerable under payment is evident.

Table – 6 :  Discrepancies by PIAs

| Implementing Agency | % actual v/s reported beneficiaries | %actual man days v/s reported man days | % actual wages v/s reported payment |
| --- | --- | --- | --- |
| GPs | 69.50 | 48.57 | 41.46 |
| Panchayat Samities | 63.55 | 46.35 | 44.78 |
| Line Dept | 100.0 | 18.37 | 22.48 |
| Overall | 68.64 | 47.56 | 41.81 |

e)  Discrepancies by Region

The 19 sample districts were classified into four regions viz. KBK, Southern, Western and North Western districts and an analysis was made to compare their performance under the three main indicators.    The results ae presented in Table – 7.  It is most distressing to see that the KBK districts were placed in a very poor light in respect of all the three indicators.   North western districts comprising Mayurbhanj, Khendjar and Dhenkanal also fared very badly, while Southern districts viz. Ganjam and Gajapathy fared well.

Table – 7 :  Region-wise discrepancies

| Region | % actual v/s reported beneficiaries | % actual man days v/s reported man days | % actual wages v/s reported payment |
| --- | --- | --- | --- |
| KBK:(Bolangir, Kalahandi,Koraput, Malkangiri, Naurangpur,Nuapada) | 56.36 | 33.00 | 26.01 |
| Southern: (Ganjam, Gajapathy) | 86.60 | 85.04 | 75.14 |
| Western: (Boudh.Deogarh,Jharsuguda,Kandhmal,Sambalpur,Sundergarh) | 82.57 | 54.5 | 55.17 |
| North Western: (Mayurbhanj, Khendjar, Dhenkanal) | 65.84 | 44.03 | 40.77 |
| Overall | 68.64 | 47.56 | 41.81 |

7.4   Reasons for Discrepancies in Muster Roll

The various discrepancies narrated above were discussed with officials, Panchayati Raj representatives and grass roots workers.  Several explanations were provided which were cross-checked and verified with documents and concerned persons.  Based on this exercise, the following three broad categories of explanations/ reasons have been arrived at.

- Expenses actually incurred but irregular entry

- System deficiencies

- Irregular practices

These are described in detail below.

a)  Expenses incurred but irregular entries

1.  Material cost booked against wages:

Many works (eg. Cement concrete road, cement platform, building) involving high material component have been taken up under NREGS.  Sometimes, the material cost is to the tune of 80- 85 percent.  The excess over permissible 40% is booked as wages against some job card holder showing higher wage payment where as there was actually no or only some payment was made to the worker.

2.  Incomplete work- dropping of workers midway:

Many a times, workers drop out and do not turn up after starting a work.  Such mid-way dropping of worker leaves works incomplete.   In their anxiety to complete the work, other workers were engaged (job card holder or otherwise) to complete the unfinished work.  Since there is no provision to show more than  100 days for a worker in the on-line data, such extra days and non job card holders wages were shown against some other  job card holders who actually did not work or worked only a few days.  Such instances are reported to be more common in line department works.

3.  Wages earned is more than Minimum wages

In piece rate works, where wages are paid according to the work ‘out turn’, actual entry in muster roll is total amount paid divided by minimum wages.  There were several instances where the wages earned in a day under piece rate basis was higher than minimum wages.  But the entry of mandays using minimum wages resulted in inflated number of days against such workers.

4.  Whole wages under piece rate charged to leader

In piece rate works, usually a group of four or five including men & women work.  While posting the wages paid to the work, entries have been made only against the labour leader but not vice-versa.  Usually the group members were not able to recollect the exact number of days.

b.  System Deficiencies

1.  Defective job cards.  The job cards printed for Phase I districts did not have a provision for recording wages paid, (since rectified in Phase II districts) and, therefore, proper entries were missing.  This led to mis interpretation by some observers.

2.  On-line entry limitation:  Inadequate staff and other provision at block/ district for day to day entry of information on line resulted in non-updating of records.  Any one who wanted to cross-check information on line with job card or muster roll, sometimes, got erroneous impression.  This was particularly true because of non-provision to record the days/ wages when some worked beyond 100 days, which was very common with line department works, such days/ wages were shown against some other job card holders.

3.  Engaging non-job card holders:  There was a misunderstanding (still continuing) that only BPL families should be given a job card.  If any persons wants to register for job card, it was not accepted or kept in abeyance for want of ‘ID number’ as per BPL.  Nevertheless, such non-job card holders were provided worker but entries made in some other job card holders.

c.  Irregular Practices

While the reasons listed under the above two categories provided a ‘benefit of doubt’ for the observed discrepancies, there were some irregular practices.

1.  Over measurement

There were many instances where over measurement was recorded and accordingly the muster rolls were inflated.  In the case of farm ponds, a certain fixed amount was given to farmers to create the farm pond while the muster rolls had shown 25 – 30% higher amount.

2.  Addition of bogus names:  Since the contractors were prohibited, the widely prevalent P C system (percentage system) had become difficult.  In order to overcome this hurdle, 25-30% bogus/ ghost names were added to muster rolls.  Dead persons, migrated people, overaged persons (80 + years), invalid persons etc. have became handy for this purpose.

3.  Outside labour through contractors.  Though contractors were prohibited, it continued in some form or other.  Even the Village Labour Leader approved by the Government was a form of contractor.  Usually these contractors bring outside labour and complete the works.  Wages were, however, shown against some job card holders.

4.  Spill over works

With the introduction of NREGS, other schemes like SGSRY got subsumed in the new scheme.  There were spill-over works NFFW Scheme also.  While these works continued (continues even after two years in some districts) wages were paid as per old rates but booked under NREGS rates.

5.  Fake Muster Rolls

Muster rolls without numbers, muster rolls with same numbers, closed muster rolls without signature of workers, closed muster rolls with signatures but not entry of wages or number of days of work, closed muster rolls only with a few signature etc. were clear example of irregularities.  In some remote GPs, the muster rolls contained 80-90% signatures.  While this is probable, considering the literacy rate in the state,  it may not be true.  There were instances, which were quite common, to have muster rolls with fully filled names i.e. 10 or its multiples.   Again, this is probable and possibly not true.  Live muster rolls were invariably absent at the work sites.

6.  Disproportionate Withdrawal of Amount from Bank

There were cases where amount withdrawn from the bank was much higher than wages to paid during the period and also amounts are withdrawn much earlier than the period of work while payment done later. Huge cash balances with GP was observed in some places giving room for suspecision on the use of these amounts.

Remarkable Turnaround in 2007-08

It is quite heartening and encouraging to see that NREGS implementation has seen a  very impressive improvement in 2007-08 over 2006-07.  Most significant outcome noticed was that the actual wages reaching the beneficiaries rose to 62 percent in 2007-08 from mere 33 in 2006-07 (Table -8)

Table – 8 : SIGNIFICANT IMPROVEMENT IN NREGS IMPLEMENTATION IN 2007-08

| Sl. No. | Indicators | 2006-2007 | 2007-2008 |
| --- | --- | --- | --- |
| 1. | Total Beneficiaries | 8912 | 2522 |
| 2. | Sample beneficiaries | 4237 | 4237 |
| 3. | Actual beneficiaries | 2455 | 1739 |
| 4. | % of actual beneficiary | 57.7 | 91.4 |
| 5. | Ghost workers | 42.3 | 8.6 |
| 6. | Total mandays | 175932 | 41069 |
| 7. | Sample mandays | 81602 | 28623 |
| 8. | Actual mandays | 30247 | 21779 |
| 9. | % actual mandays | 37.1 | 76.9 |
| 10. | % of ghost mandays | 62.9 | 23.1 |
| 11. | Total wage payment in RS | 5465710 | 2376121 |
| 12. | Wages Received by workers | 1807200 | 1461880 |
| 13. | % actual wages paid | 33.1 | 61.5 |

8.  Major Conclusions

NREGS implementation, in the initial year, faced several teething problems including huge spill over works.  The contractor syndrome and preference for high material cost works etc. posed challenges to meet the guidelines requirement of NREGS.  Inadequate orientation to the provisions of NREGS, poor staff strength, inappropriate planning and priorities etc. led to several violations of the provisions of the NREGA.  Lack of awareness building among the communities, patronage of certain sections, specific oral instructions on some priorities etc. limited the access of the programme to large section of the rural  communities.  In view of this several irregularities, some by mistake, some by system defects and some by design, came to the fore.  Major shortcomings included, non-registration of workers, not providing work on demand, ghost workers, a ghost works (very small, though), lesser wages actually reaching the workers, bogus muster rolls etc.  Studies by civil society organizations and others highlighted the deficiencies and shortcomings which received wide media coverage.  This has alerted the state and district administrations. Immediate follow-up measures and corrective actions including provision of staff have showed remarkable improvement in the performance and outcome indicators of the scheme during 2007-08.  Despite the observed irregularities,  it was  heartening to note that more than 95% of the projects reported to have taken up under NREGS were found to be correct and true.   The actual wages reaching beneficiaries rose to 62% from 33% in 2006-07.  The efforts of the government needs to be commended in this regard.  There are signals that things will improve further.  There appears to be a political will too.  Though the programme implementation has shown appreciable improvement, the gaps are still wide and need immediate attention.  It is a matter of great concern that the most poor KBK districts witnessed poorest implementation record.  The Social Audit processes received overwhelming response from the community and there is a demand for on-going social audits.

9.  Recommendations:

1.  Intensive publicity campaign to build awareness of communities on their rights and entitlements is needed.   The NGO network associated with the Social Audit can be very effectively used for this purpose

2.  Refresher training in old districts and very intensive training in new districts covering officials, non-officials and line departments associated with NREGS may be planned and organized in a crash manner.  The common failings brought out by social audit should be discussed in such training.

3.  The Social Audit process will become meaningless if there is no follow-up action.  In order to restore faith on the government among communities, appropriate corrective action including recoveries and disciplinary proceedings are called for.  As a first step, it is necessary to ensure that all deficiencies are rectified in the 40 GPs where social audit was carried out.

4.  Wherever material intensive works are taken up under instructions from state or district administration, such works should be taken up only with convergence eg. CC roads can be converged with XII Finance Commission, Panchayat Ghars with XII Finance Commission and BRGF.

5.  There should be frequent audit of accounts and registers of NREGS by the district/ state audit agencies.

6.  The Vigilance and Monitoring Committees should be reconstituted, trained and empowered to keep a watch on NREGS implementation.  The compositions of VMCs should comprise representatives from all major political parties, SHGs, CSOs and local NGO in order to make it effective.

7.  The Social Audit should be institutionalized to be a regular activity.  The experience suggest that an external/ independent agency may be needed to ensure that the social audit is not initiated.  While an empowered VMC would be  useful institution, training some local youth to be social auditors may help the expenses on social audit to be kept at a reasonable level.

8.  There is a need to streamline and intensify NREGS monitoring.  The new guidelines of NREGS stipulates 100% verification of muster rolls.  Using official machinery for this purpose may not yield desired results.  Involving civil society organizations may be considered.  As part of regular monitoring, specific tasks and relevant formats may be designed for Collectors, PDs, BDOs, Sectoral Heads of related line departments and ensure that these officials send feed back to district and state levels.  The follow-up and corrective action should also be documented.

9. Payment of wages through Bank, Post Offices and other institutions should be very carefully planned, implemented and monitored.

10.  Arrangement  for ‘on-line’ posting information need to be reviewed and deficiencies rectified.  The best practices in some GPs could be a site for exposure visit to GP level implementing personnel.

11.  The KBK districts deserve special attention in monitoring, supervision and follow-up action.  Special monitors may be appointed to check things and bring all those involved in irregularities to book.

12.  DPCs should expeditiously approve and clear projects so that GPs have continuous works going on in their areas to provide work to all the needy people.  The line departments should take up work only when the work is approved in Gram Sabha and Panchayat Samities so that PRIs are in the know of these works and also give the details of workers to be engaged.

Annexure – 1 : District wise Implementing Agency of Audited Works

|  | Implementing Agency |  |  | Total |
| --- | --- | --- | --- | --- |
|  | Gram Panchayat | Panchayat Samiti | Soil conseravation Dept. |  |
| Bolangir | 6 | 3 |  | 9 |
|  | 66.7% | 33.3% |  | 100.0% |
| Boudh | 2 | 1 |  | 3 |
|  | 66.7% | 33.3% |  | 100.0% |
| Deogarh | 2 | 1 |  | 3 |
|  | 66.7% | 33.3% |  | 100.0% |
| Dhenkamal | 4 |  |  | 4 |
|  | 100.0% |  |  | 100.0% |
| Gajapati | 4 | 2 |  | 6 |
|  | 66.7% | 33.3% |  | 100.0% |
| Ganjam | 7 | 2 |  | 9 |
|  | 77.8% | 22.2% |  | 100.0% |
| Jharsuguda | 3 |  |  | 3 |
|  | 100.0% |  |  | 100.0% |
| Kalahandi | 3 | 2 |  | 5 |
|  | 60.0% | 40.0% |  | 100.0% |
| Kandhamal | 4 |  |  | 4 |
|  | 100.0% |  |  | 100.0% |
| Kendujhar | 7 | 1 |  | 8 |
|  | 87.5% | 12.5% |  | 100.0% |
| Koraput | 9 |  |  | 9 |
|  | 100.0% |  |  | 100.0% |
| Malkangiri | 5 | 1 |  | 6 |
|  | 83.3% | 16.7% |  | 100.0% |
| Mayurbhanj | 11 | 1 |  | 12 |
|  | 91.7% | 8.3% |  | 100.0% |
| Nabarangpur | 3 | 3 | 1 | 7 |
|  | 42.9% | 42.9% | 14.3% | 100.0% |
| Nuapada | 1 |  |  | 1 |
|  | 100.0% |  |  | 100.0% |
| Rayagada | 1 | 3 |  | 4 |
|  | 25.0% | 75.0% |  | 100.0% |
| Sambalpur | 6 | 3 |  | 9 |
|  | 66.7% | 33.3% |  | 100.0% |
| Sundergarh | 6 | 3 |  | 9 |
|  | 66.7% | 33.3% |  | 100.0% |
|  | 84 | 26 | 1 | 111 |
|  | 75.7% | 23.4% | .9% | 100.0% |

Annexure – 2 : District Wise year of Implementation of Audited Works

|  | Year of Implementation |  |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- |
|  | 2005-06 | 2006-07 | 2006-08 | 2007-08 | 2007-09 |  |
| Bolangir | 1 | 5 | 1 | 2 |  | 9 |
|  | 11.1% | 55.6% | 11.1% | 22.2% |  | 100.0% |
| Boudh |  | 2 | 1 |  |  | 3 |
|  |  | 66.7% | 33.3% |  |  | 100.0% |
| Deogarh |  | 2 |  | 1 |  | 3 |
|  |  | 66.7% |  | 33.3% |  | 100.0% |
| Dhenkamal |  | 3 |  |  | 1 | 4 |
|  |  | 75.0% |  |  | 25.0% | 100.0% |
| Gajapati |  | 2 | 2 | 2 |  | 6 |
|  |  | 33.3% | 33.3% | 33.3% |  | 100.0% |
| Ganjam |  |  |  | 9 |  | 9 |
|  |  |  |  | 100.0% |  | 100.0% |
| Jharsuguda |  | 2 |  | 1 |  | 3 |
|  |  | 66.7% |  | 33.3% |  | 100.0% |
| Kalahandi |  | 5 |  |  |  | 5 |
|  |  | 100.0% |  |  |  | 100.0% |
| Kandhamal |  | 4 |  |  |  | 4 |
|  |  | 100.0% |  |  |  | 100.0% |
| Kendujhar |  | 8 |  |  |  | 8 |
|  |  | 100.0% |  |  |  | 100.0% |
| Koraput |  | 7 |  | 2 |  | 9 |
|  |  | 77.8% |  | 22.2% |  | 100.0% |
| Malkangiri |  | 4 |  | 2 |  | 6 |
|  |  | 66.7% |  | 33.3% |  | 100.0% |
| Mayurbhanj |  | 1 | 1 | 10 |  | 12 |
|  |  | 8.3% | 8.3% | 83.3% |  | 100.0% |
| Nabarangpur |  | 5 |  | 2 |  | 7 |
|  |  | 71.4% |  | 28.6% |  | 100.0% |
| Nuapada |  |  |  | 1 |  | 1 |
|  |  |  |  | 100.0% |  | 100.0% |
| Rayagada |  | 2 |  | 2 |  | 4 |
|  |  | 50.0% |  | 50.0% |  | 100.0% |
| Sambalpur |  | 7 |  | 2 |  | 9 |
|  |  | 77.8% |  | 22.2% |  | 100.0% |
| Sundergarh |  | 9 |  |  |  | 9 |
|  |  | 100.0% |  |  |  | 100.0% |
|  | 1 | 68 | 5 | 36 | 1 | 111 |
|  | .9% | 61.3% | 4.5% | 32.4% | .9% | 100.0% |

Annexure – 3 : District Wise Status of Audited Works

|  | STATUS |  | Total |
| --- | --- | --- | --- |
|  | Completed | Ongoing |  |
| Bolangir | 7 | 2 | 9 |
|  | 77.8% | 22.2% | 100.0% |
| Boudh | 3 |  | 3 |
|  | 100.0% |  | 100.0% |
| Deogarh | 1 | 2 | 3 |
|  | 33.3% | 66.7% | 100.0% |
| Dhenkamal | 3 | 1 | 4 |
|  | 75.0% | 25.0% | 100.0% |
| Gajapati | 6 |  | 6 |
|  | 100.0% |  | 100.0% |
| Ganjam | 4 | 5 | 9 |
|  | 44.4% | 55.6% | 100.0% |
| Jharsuguda | 3 |  | 3 |
|  | 100.0% |  | 100.0% |
| Kalahandi | 5 |  | 5 |
|  | 100.0% |  | 100.0% |
| Kandhamal | 4 |  | 4 |
|  | 100.0% |  | 100.0% |
| Kendujhar | 8 |  | 8 |
|  | 100.0% |  | 100.0% |
| Koraput | 9 |  | 9 |
|  | 100.0% |  | 100.0% |
| Malkangiri | 4 | 2 | 6 |
|  | 66.7% | 33.3% | 100.0% |
| Mayurbhanj | 4 | 8 | 12 |
|  | 33.3% | 66.7% | 100.0% |
| Nabarangpur | 5 | 2 | 7 |
|  | 71.4% | 28.6% | 100.0% |
| Nuapada | 1 |  | 1 |
|  | 100.0% |  | 100.0% |
| Rayagada | 1 | 3 | 4 |
|  | 25.0% | 75.0% | 100.0% |
| Sambalpur | 4 | 5 | 9 |
|  | 44.4% | 55.6% | 100.0% |
| Sundergarh | 4 | 5 | 9 |
|  | 44.4% | 55.6% | 100.0% |
| Total | 76 | 35 | 111 |
|  | 68.5% | 31.5% | 100.0% |

Annexure. 4.  Social Audit Details / Volunteers

| District | Block | Panchayat | No of Volunteers | Training date(s) | Social Audit date | Organisation |
| --- | --- | --- | --- | --- | --- | --- |
| Bolangir | Agalpur | Duduka | 11 | 18-01-08to20-01-08 | 4-02-08 | Vikash Pratisthan, Bonai & Sweak, Sundargarh |
|  | Belpara | Gambhari | 11 | 18-01-08to20-01-08 | 2-02-08 | Samuhik Marudi Pratikar, Udyam , Bolangir |
|  | Titlagarh | Bijepur | 12 | 18-01-08to20-01-08 | 1-02-08 | Samuhik Marudi Pratikar, Udyam , Bolangir |
| Boudh | Kantamal | Similipadar | 12 | 18-01-08to20-01-08 | 27-02-08 | YCDA, Boudh |
| Deogarh | Barkote | Saruali | 10 | 7-03-08 | 14-03-08 | Sahajog, Deogarh |
| Dhenkanal | Hindol | Baunsa Pokhari | 8 | 20-4-08 to 21-4-08 | 28-04-08 | Adibasi Kranti Sangathan & Ganeswar Club, Dhenkanal |
|  | Kankadahad | Kantapal | 13 | 20-4-08 to 21-4-08 | 29-04-04 | Adibasi Kranti Sangathan & Ganeswar Club, Dhenkanal |
| Gajapati | Kasinagar | Siali | 12 | 8-03-08 | 20-03-08 | SWWS, Gajapati |
|  | Mohona | Chandiput | 14 | 8-03-08 | 19-03-08 | SWWS, Gajapati |
| Ganjam | Kukudakhandi | Sihala | 10 | 16-03-08 | 28-03-08 | UAA, Ganjam |
|  | Surada | Asurabandha | 7 | 16-03-08 | 2-04-04 | UAA, Ganjam |
|  | Sheragada | Mahupadar | 10 | 16-03-08 | 26-03-08 | UAA, Ganjam |
| Jharsuguda | Lakhanpur | Panchagaon | 15 | 23-05-08 | 29-05-08 | Development Initiative & Sruti |
| Kalahandi | Bhawanipatna | Artal | 13 | 18-01-08 to 20-01-08 | 1-02-08 | Rupayaan, Kalahandi |
|  | Karlamunda | Joradobra | 12 | 18-01-08to20-01-08 | 27-01-08 | Rupayaan, Kalahandi |
| Kandhamal | Phiringia | Luisingi | 10 | 19-05-08 | 26-05-08 | Nipidit, Kandhmal |
|  | Tikabali | Gutingia | 9 | 19-05-08 | 27-05-08 | Nipidit, Kandhmal |
| Kendujhar | Ghatgaon | Sarasa Pasi | 7 | 1-03-08 | 25-03-08 | WOSCA, Kendujhar |
|  | Kendujhar Sadar | Raikala | 7 | 1-03-08 | 20-03-08 | WOSCA, Kendujhar |
|  | Saharapada | Malarpada | 6 | 1-03-08 | 18-03-08 | WOSCA, Kendujhar |
| Koraput | Borigumma | Pondasguda | 13 | 18-01-08to20-01-08 | 31-01-08 | Spread, Koraput |
|  | Nandapur | Khurji | 14 | 18-01-08to20-01-08 | 1-02-08 | Spread, Koraput |
|  | Bandhugaon | Nilabadi | 14 | 18-01-08to20-01-08 | 2-02-08 | Spread, Koraput |
| Malkangiri | Korukonda | Nuaguda | 14 | 03-03-08-04-03-08 | 19-03-08 | Rites Forum, Malkangiri |
|  | Malkangiri | Gangala | 10 | 03-03-08-04-03-08 | 16-03-08 | Rites Forum, Malkangiri |
| Mayurbhanj | Gopabandhunagar | Arapata | 12 | 8.5.2008 | Cancelled | BSSS, Balasore |
|  | Badasahi | Chandanpur | 11 | 8-05-2008 | 15-05-08 | BSSS, Balasore |
|  | Saraskana | Murunia | 8 | 8-05-08 | 16-05-08 | BSSS, Balasore |
|  | Rasgovindpur | Debasole | 11 | 8-05-08 | 16-05-08 | BSSS, Balasore |
| Nabarangpur | Papadahandi | Papadahandi | 10 | 28-02-08 | 13-03-08 | Nabchetna Network, Nabrangpur |
|  | Chandahandi | Gambariguda | 9 | 28-02-08 | 11-03-08 | Nabchetna Network, Nabrangpur |
| Nuapada | Sinapali | Ghatamal | 9 | 18.1.08 to 20.1.08 | 3-02-08 | Lkdrusti, Nuapada |
| Rayagada | Rayagada | Gumma | 13 | 20.5.08 | 26-05-08 | OPDSC, Rayagada |
|  | Chandrapur | Piskapanga | 15 | 20.05.08 | 27-05-08 | OPDSC, Rayagada |
| Sambalpur | Kuchinda | Hadipali | 11 | 8-03-08 | 17-03-08 | Lok Bikas, Sambalpur |
|  | Rairakhol | Badbahal | 10 | 11-03-08 | 28-03-08 | Lok Bikas, Sambalpur |
| Subarnapur | Biramaharajpur | Mursundhi | 13 | 18.1.08 to 20.1.08 | 01-02-08 | Rare, Sonepur |
| Sundergarh | Bargaon | Ekma | 10 | 07-03-08 | 15-03-08 | Sewak, Sundergarh & KBP, Badgaon |
|  | Kutra | Ambhagova | 10 | 07-03-08 | 14-03-08 | Sewak, Sundergarh & Angana, kutra |
|  | Bonaigarh | Sarsara Balang | 9 | 07-03-08 | 16-03-08 | Vikash Pratisthan, Bonai & Sewak , Sundergarh |
| 19 | 40 | 40 | 435* |  |  |  |

* = The number of volunteer is not absolute as many volunteers participated in more than one social audit. The  actual number of volunteers involved in the whole process is less than 435.

Annexure. 5.  Household Enumeration on NREGS Registration Details

| Sl | Block | Panchayat | GP Record |  |  | Survey detail |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total HH | Regd HH | % | Surveyed HH | Regd HH | % |
| 1 | Agalpur | Duduka |  |  |  | 1753 | 821 | 46.83% |
| 2 | Belpara | Gambhari |  |  |  | 953 | 480 | 50.37% |
| 3 | Titlagarh | Bijepur | 2252 | 1155 | 51.28% | 1734 | 1021 | 58.88% |
| 4 | Kantamal | Similipadar | 1588 | 1202 | 75.69% | 1252 | 864 | 69.01% |
| 5 | Barkote | Saruali | 1298 | 1184 | 91.21% | 738 | 608 | 82.38% |
| 6 | Hindol | Baunsa Pokhari | 863 | 296 | 34.30% | 763 | 235 | 30.79% |
| 7 | Kankadahad | Kantapal | 1296 |  |  | 613 | 272 | 44.37% |
| 8 | Kasinagar | Siali | 1455 | 1455 | 100% | 1104 | 672 | 60.87% |
| 9 | Mohona | Chandiput | 1208 | 1078 | 89% | 1099 | 857 | 77.97% |
| 10 | Kukudakhandi | Sihala | 1493 | 1616 | 108 | 1178 | 604 | 51.27% |
| 11 | Surada | Asurabandha | 1590 | 1100 | 69.18% | 1695 | 706 | 41.65% |
| 12 | Sheragada | Mahupadar | 1947 | 983 | 50.48% | 1425 | 555 | 38.94% |
| 13 | Lakhanpur | Panchagaon | 550 | 508 | 92.36 | 219 | 209 | 95.43% |
| 14 | Bhawanipatna | Artal | 2120 | 1389 | 65.51% | 1863 | 791 | 42.45% |
| 15 | Karlamunda | Joradobra | 1375 | 994 | 72.29% | 1309 | 802 | 61.26% |
| 16 | Phiringia | Luisingi |  | 852 |  | 293 | 291 | 99.31% |
| 17 | Tikabali | Gutingia | 1152 | 962 | 83.50% | 516 | 458 | 88.75% |
| 18 | Ghatgaon | Sarasa Pasi | 619 | 613 | 99.03% | 578 | 505 | 87.37% |
| 19 | Kendujhar Sadar | Raikala | 988 | 510 | 51.61% | 1045 | 221 | 21.14% |
| 20 | Saharapada | Malarpada | 1405 | 2116 | 150.60% | 1292 | 879 | 68.03% |
| 21 | Borigumma | Pondasguda | 883 | 491 | 55.60% | 883 | 491 | 55.06% |
| 22 | Nandapur | Khurji | 1076 | 879 | 81.69% | 1076 | 879 | 81.69% |
| 23 | Bandhugaon | Nilabadi | 949 | 864 | 91.04% | 949 | 864 | 91.04% |
| 24 | Korukonda | Nuaguda | 683 | 673 | 98.53% | 610 | 535 | 87.70% |
| 25 | Malkangiri | Gangala | 738 | 637 | 86.31% | 768 | 513 | 66.79% |
| 26 | Gopabandhunagar | Arapata | 1276 | 1130 | 88.55% | 413 | 364 | 88.14% |
| 27 | Badasahi | Chandanpur |  | 918 |  | 414 | 339 | 81.88% |
| 28 | Saraskana | Murunia | 1313 | 881 | 67.09% | 414 | 376 | 90.82% |
| 29 | Rasgovindpur | Debasole | 1202 | 795 | 66.13% | 541 | 405 | 74.86% |
| 30 | Papadahandi | Papadahandi |  |  |  | 1103 | 754 | 68.35% |
| 31 | Chandahandi | Gambariguda | 1483 | 970 | 65.40% | 1236 | 775 | 62.70% |
| 32 | Sinapali | Ghatamal | 851 | 720 | 84.60% | 681 | 610 | 89.57% |
| 33 | Rayagada | Gumma |  |  |  | 439 | 430 | 97.95% |
| 34 | Chandrapur | Piskapanga |  |  |  | 706 | 459 | 65.01% |
| 35 | Kuchinda | Hadipali | 837 | 706 | 84.34% | 669 | 491 | 73.39% |
| 36 | Rairakhol | Badbahal |  |  |  | 780 | 495 | 63.46% |
| 37 | Biramaharajpur | Mursundhi | 2058 | 1750 | 85.03% | 1861 | 709 | 38.10% |
| 38 | Bargaon | Ekma | 1544 | 1543 | 99.93% | 744 | 599 | 80.51% |
| 39 | Kutra | Ambhagova | 1552 | 1522 | 98.06% | 1012 | 706 | 69.67% |
| 40 | Bonaigarh | Sarsara Balang | 1621 | 1600 | 98.70% | 994 | 796 | 80.08% |
|  | 40 | 40 |  |  |  | 37715 | 23441 | 62.15% |

Note: the blank rows indicate non availability of information

Annexure.6    Household Enumeration on NREGS Job Card Details

| Sl | Block | Panchayat | GP Record |  |  | Survey detail |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total HH | HH having job cards | % | Surveyed HH | HH having job cards | % |
| 1 | Agalpur | Duduka |  |  |  | 1753 | 867 | 49.45% |
| 2 | Belpara | Gambhari |  |  |  | 953 | 250 | 26.23% |
| 3 | Titlagarh | Bijepur | 2252 | 1151 | 51.11% | 1734 | 933 | 53.80% |
| 4 | Kantamal | Similipadar | 1202 | 1050 | 87.35% | 1252 | 774 | 61.82% |
| 5 | Barkote | Saruali | 1298 | 1184 | 91.21% | 738 | 517 | 70.05% |
| 6 | Hindol | Baunsa Pokhari | 863 | 288 | 33.37% | 763 | 184 | 24.12% |
| 7 | Kankadahad | Kantapal | 1296 | 920 | 70.98% | 613 | 415 | 67.69% |
| 8 | Kasinagar | Siali | 1455 | 1129 | 77.59% | 1104 | 441 | 39.95% |
| 9 | Mohona | Chandiput | 1208 | 1072 | 88.74% | 1099 | 852 | 77.52% |
| 10 | Kukudakhandi | Sihala | 1493 | 1616 | 108.24% | 1178 | 604 | 51.30% |
| 11 | Surada | Asurabandha | 1590 | 1100 | 69.18% | 1695 | 529 | 31.20% |
| 12 | Sheragada | Mahupadar | 1947 | 983 | 50.49% | 1425 | 741 | 52.00% |
| 13 | Lakhanpur | Panchagaon | 550 | 509 | 92.95% | 219 | 202 | 92.24% |
| 14 | Bhawanipatna | Artal | 2120 | 896 | 42.26% | 1863 | 688 | 36.92% |
| 15 | Karlamunda | Joradobra | 1375 | 984 | 71.56% | 1309 | 802 | 61.26% |
| 16 | Phiringia | Luisingi |  | 846 |  | 293 | 286 | 97.61% |
| 17 | Tikabali | Gutingia | 1152 | 860 | 74.65% | 516 | 421 | 81.58% |
| 18 | Ghatgaon | Sarasa Pasi | 619 | 613 | 99.03% | 578 | 443 | 76.64% |
| 19 | Kendujhar Sadar | Raikala | 988 | 751 | 57.79% | 1045 | 149 | 14.52% |
| 20 | Saharapada | Malarpada | 1405 | 564 | 40.14% | 1292 | 564 | 43.65% |
| 21 | Borigumma | Pondasguda | 883 | 334 | 37.82% | 883 | 334 | 37.82% |
| 22 | Nandapur | Khurji | 1076 | 879 | 81.69% | 1076 | 879 | 81.69% |
| 23 | Bandhugaon | Nilabadi | 949 | 679 | 91.04% | 949 | 679 | 91.04% |
| 24 | Korukonda | Nuaguda | 683 | 484 | 70.86% | 610 | 427 | 70% |
| 25 | Malkangiri | Gangala | 738 | 593 | 80.35% | 768 | 415 | 54.03% |
| 26 | Gopabandhunagar | Arapata | 1236 | 738 | 59.70% | 413 | 304 | 73.60% |
| 27 | Badasahi | Chandanpur |  | 1068 |  | 414 | 335 | 80.91% |
| 28 | Saraskana | Murunia | 1313 | 783 | 60.00% | 414 | 376 | 82.00% |
| 29 | Rasgovindpur | Debasole | 1202 | 667 | 55.49% | 541 | 324 | 59.89% |
| 30 | Papadahandi | Papadahandi |  |  |  | 1103 | 718 | 65% |
| 31 | Chandahandi | Gambariguda | 1483 | 940 | 63.38% | 1236 | 723 | 58.49% |
| 32 | Sinapali | Ghatamal | 851 | 742 | 87.19% | 681 | 616 | 90.45% |
| 33 | Rayagada | Gumma |  |  |  | 439 | 429 | 97.72% |
| 34 | Chandrapur | Piskapanga |  |  |  | 706 | 289 | 40.93% |
| 35 | Kuchinda | Hadipali | 837 | 706 | 84.34% | 669 | 453 | 67.71% |
| 36 | Rairakhol | Badbahal |  |  |  | 780 | 406 | 52.05% |
| 37 | Biramaharajpur | Mursundhi | 2058 | 943 | 45.82% | 1861 | 470 | 25.26% |
| 38 | Bargaon | Ekma | 1544 | 1543 | 99.93% | 744 | 599 | 80.51% |
| 39 | Kutra | Ambhagova | 1552 | 1501 | 96.71% | 1012 | 700 | 69.16% |
| 40 | Bonaigarh | Sarsara Balang | 1621 | 1368 | 84.39% | 994 | 762 | 76.65% |
|  | 40 | 40 |  |  |  | 37715 | 20900 | 55.41% |

Note: the blank rows indicate non availability of information

Annexure – 7 : Number of Reported and Actual Beneficiaries

| District Code | BLOCK2 | GP Code | Total Beneficiaries | Surveyed Beneficiaries | Actual no of Beneficiaries |
| --- | --- | --- | --- | --- | --- |
| Bolangir | Agalpur | Duduka | 221 | 104 | 99 |
|  | Belpara | Gambhari | 249 | 68 | 61 |
|  | Titlagarh | Bijepur | 243 | 155 | 118 |
| Boudh | Kantama | Similipadar | 253 | 114 | 81 |
| Deogarh | Barkote | Saruali | 296 | 81 | 57 |
| Dhenkamal | Hindol | Baunsa Pokhari | 103 | 97 | 95 |
|  | Kankada | Kantapal | 483 | 378 | 102 |
| Gajapati | Kankada | Siali | 337 | 140 | 69 |
|  | Mohona | Chandiput | 232 | 126 | 126 |
| Ganjam | Kukudak | Sihala | 136 | 117 | 117 |
|  | Surada | Asurabandha | 109 | 109 | 109 |
|  | Sheraga | Mahupadar | 416 | 416 | 416 |
| Jharsuguda | Lakhanp | Panchagaon | 268 | 47 | 46 |
| Kalahandi | Bhawani | Artal | 501 | 153 | 23 |
|  | Karlamu | Joradobra | 466 | 68 | 29 |
| Kandhamal | Phiringia | Luisingi | 871 | 340 | 316 |
|  | Tikabali | Gulingia | 56 | 47 | 47 |
| Kendujhar | Kendujh | Raikala | 281 | 121 | 121 |
|  | Saharap | Malarpada | 257 | 197 | 142 |
|  | Ghatgaon | Sarasa Pasi | 487 | 277 | 159 |
| Koraput | Borigum | Pondasguda | 502 | 377 | 216 |
|  | Nandapu | Khurji | 417 | 417 | 376 |
|  | Bandhug | Nilabadi | 121 | 121 | 70 |
| Malkangiri | Malkangi | Gangala | 155 | 114 | 42 |
|  | Korukonda | Nuaguda | 169 | 137 | 34 |
| Mayurbhanj | Gopaba | Arapata | 131 | 131 | 131 |
|  | Badasah | Chandanpur | 289 | 109 | 72 |
|  | Saraska | Murunia | 261 | 108 | 108 |
|  | Rasgovi | Debasole | 188 | 180 | 158 |
| Nabarangpur | Papadah | Papadahandi | 373 | 195 | 152 |
|  | Chandah | Gambariguda | 299 | 248 | 184 |
| Nuapada | Sinapali | Ghalamal | 32 | 23 | 23 |
| Rayagada | Rayagad | Gumma | 139 | 76 | 51 |
|  | Chandra | Piskapanga | 184 | 74 | 33 |
| Sambalpur | Kuchind | Hadipali | 399 | 147 | 136 |
|  | Rairakho | Badbahal | 338 | 132 | 88 |
|  | Biramahar | Mursundhi | 724 | 422 | 50 |
| Sundergarh | Kutra | Ambhagova | 318 | 111 | 102 |
|  | Bonarigar | Sarsara Balang | 274 | 71 | 33 |
|  | Baragaon | Ekma | 590 | 164 | 149 |

Annexure 8:  GP wise reported and Actual Beneficiaries

| District code | BLOCK2 | gpcode | Total Beneficiaries | Surveyed Beneficiaries | Actual no of Beneficiaries | % (Actual/Surveyed Bene.) |
| --- | --- | --- | --- | --- | --- | --- |
| Bolangir | Agalpur | Duduka | 221 | 104 | 99 | 95.19 |
|  | Belpara | Gambhari | 249 | 68 | 61 | 89.71 |
|  | Titlagarh | Bijepur | 243 | 155 | 118 | 76.13 |
| Boudh | Kantama | Similipadar | 253 | 114 | 81 | 71.05 |
| Deogarh | Barkote | Saruali | 296 | 81 | 57 | 70.37 |
| Dhenkamal | Hindol | Baunsa Pokhari | 103 | 97 | 95 | 97.94 |
|  | Kankada | Kantapal | 483 | 378 | 102 | 26.98 |
| Gajapati | Kankada | Siali | 337 | 140 | 69 | 49.29 |
|  | Mohona | Chandiput | 232 | 126 | 126 | 100.00 |
| Ganjam | Kukudak | Sihala | 136 | 117 | 117 | 100.00 |
|  | Surada | Asurabandha | 109 | 109 | 109 | 100.00 |
|  | Sheraga | Mahupadar | 416 | 416 | 416 | 100.00 |
| Jharsuguda | Lakhanp | Panchagaon | 268 | 47 | 46 | 97.87 |
| Kalahandi | Bhawani | Artal | 501 | 153 | 23 | 15.03 |
|  | Karlamu | Joradobra | 466 | 68 | 29 | 42.65 |
| Kandhamal | Phiringia | Luisingi | 871 | 340 | 316 | 92.94 |
|  | Tikabali | Gulingia | 56 | 47 | 47 | 100.00 |
| Kendujhar | Kendujh | Raikala | 281 | 121 | 121 | 100.00 |
|  | Saharap | Malarpada | 257 | 197 | 142 | 72.08 |
|  | Ghatgaon | Sarasa Pasi | 487 | 277 | 159 | 57.40 |
| Koraput | Borigum | Pondasguda | 502 | 377 | 216 | 57.29 |
|  | Nandapu | Khurji | 417 | 417 | 376 | 90.17 |
|  | Bandhug | Nilabadi | 121 | 121 | 70 | 57.85 |
| Malkangiri | Malkangi | Gangala | 155 | 114 | 42 | 36.84 |
|  | Korukonda | Nuaguda | 169 | 137 | 34 | 24.82 |
| Mayurbhanj | Gopaba | Arapata | 131 | 131 | 131 | 100.00 |
|  | Badasah | Chandanpur | 289 | 109 | 72 | 66.06 |
|  | Saraska | Murunia | 261 | 108 | 108 | 100.00 |
|  | Rasgovi | Debasole | 188 | 180 | 158 | 87.78 |
| Nabarangpur | Papadah | Papadahandi | 373 | 195 | 152 | 77.95 |
|  | Chandah | Gambariguda | 299 | 248 | 184 | 74.19 |
| Nuapada | Sinapali | Ghalamal | 32 | 23 | 23 | 100.00 |
| Rayagada | Rayagad | Gumma | 139 | 76 | 51 | 67.11 |
|  | Chandra | Piskapanga | 184 | 74 | 33 | 44.59 |
| Sambalpur | Kuchind | Hadipali | 399 | 147 | 136 | 92.52 |
|  | Rairakho | Badbahal | 338 | 132 | 88 | 66.67 |
|  | Biramahar | Mursundhi | 724 | 422 | 50 | 11.85 |
| Sundergarh | Kutra | Ambhagova | 318 | 111 | 102 | 91.89 |
|  | Bonarigar | Sarsara Balang | 274 | 71 | 33 | 46.48 |
|  | Baragaon | Ekma | 590 | 164 | 149 | 90.85 |

Annexure – 9 : GP Wise Reported and Actual Person Days

| District Code | BLOCK2 | GP Code | Total Person Days | Surveyed Person days | Actual Person days | % of Actual person/ surveyed days |
| --- | --- | --- | --- | --- | --- | --- |
| Bolangir | Agalpur | Duduka | 4861 | 2124 | 918 | 43.2 |
|  | Belpara | Gambhari | 3759 | 1544 | 1039 | 67.3 |
|  | Titlagarh | Bijepur | 5494 | 2623 | 1012 | 38.6 |
| Boudh | Kantama | Similipadar | 6892 | 2273 | 1250 | 55.0 |
| Deogarh | Barkote | Saruali | 7661 | 2679 | 786 | 29.3 |
| Dhenkamal | Hindol | Baunsa Pokhari | 1722 | 1518 | 1159 | 76.4 |
|  | Kankada | Kantapal | 10220 | 7340 | 1238 | 16.9 |
| Gajapati | Kankada | Siali | 7457 | 2552 | 1035 | 40.6 |
|  | Mohona | Chandiput | 3144 | 2174 | 2277 | 104.7 |
| Ganjam | Kukudak | Sihala | 2616 | 1987 | 1987 | 100.0 |
|  | Surada | Asurabandha | 1891 | 1891 | 1891 | 100.0 |
|  | Sheraga | Mahupadar | 6722 | 6722 | 6722 | 100.0 |
| Jharsuguda | Lakhanp | Panchagaon | 4256 | 466 | 281 | 60.3 |
| Kalahandi | Bhawani | Artal | 11076 | 4872 | 255 | 5.2 |
|  | Karlamu | Joradobra | 6010 | 1479 | 497 | 33.6 |
| Kandhamal | Phiringia | Luisingi | 15706 | 6589 | 6020 | 91.4 |
|  | Tikabali | Gulingia | 2021 | 1846 | 1334 | 72.3 |
| Kendujhar | Kendujh | Raikala | 4120 | 2087 | 671 | 32.2 |
|  | Saharap | Malarpada | 3846 | 3050 | 1176 | 38.6 |
|  | Ghatgaon | Sarasa Pasi | 9993 | 5799 | 1184 | 20.4 |
| Koraput | Borigum | Pondasguda | 10612 | 4106 | 1326 | 32.3 |
|  | Nandapu | Khurji | 4378 | 4378 | 2819 | 64.4 |
|  | Bandhug | Nilabadi | 1621 | 1578 | 803 | 50.9 |
| Malkangiri | Malkangi | Gangala | 4653 | 2693 | 586 | 21.8 |
|  | Korukonda | Nuaguda | 4597 | 3683 | 404 | 11.0 |
| Mayurbhanj | Gopaba | Arapata | 3650 | 3641 | 3633 | 99.8 |
|  | Badasah | Chandanpur | 4870 | 1829 | 718 | 39.3 |
|  | Saraska | Murunia | 2870 | 1105 | 969 | 87.7 |
|  | Rasgovi | Debasole | 3943 | 2532 | 2539 | 100.3 |
| Nabarangpur | Papadah | Papadahandi | 11164 | 5776 | 1579 | 27.3 |
|  | Chandah | Gambariguda | 4010 | 1939 | 1135 | 58.5 |
| Nuapada | Sinapali | Ghalamal | 944 | 944 | 336 | 35.6 |
| Rayagada | Rayagad | Gumma | 3060 | 1936 | 1504 | 77.7 |
|  | Chandra | Piskapanga | 4316 | 1846 | 539 | 29.2 |
| Sambalpur | Kuchind | Hadipali | 7017 | 2443 | 1389 | 56.9 |
|  | Rairakho | Badbahal | 10545 | 4615 | 1359 | 29.4 |
|  | Biramahar | Mursundhi | 10485 | 6526 | 1016 | 15.6 |
| Sundergarh | Kutra | Ambhagova | 4848 | 1482 | 943 | 63.6 |
|  | Bonarigar | Sarsara Balang | 5182 | 795 | 178 | 22.4 |
|  | Baragaon | Ekma | 9443 | 2792 | 1732 | 62.0 |

Annexure – 10 : GP Wise Reported and Actual Wage Payment

| District Code | BLOCK2 | GP Code | Wage paid to Sample bene | Actually reached the bene | % of Actually / Wage paid |
| --- | --- | --- | --- | --- | --- |
| Bolangir | Agalpur | Duduka | 119275 | 49945 | 41.87 |
|  | Belpara | Gambhari | 92236 | 60206 | 65.27 |
|  | Titlagarh | Bijepur | 144265 | 41174 | 28.54 |
| Boudh | Kantama | Similipadar | 212240 | 100485 | 47.34 |
| Deogarh | Barkote | Saruali | 225203 | 75590 | 33.57 |
| Dhenkamal | Hindol | Baunsa Pokhari | 105330 | 56700 | 53.83 |
|  | Kankada | Kantapal | 404740 | 69741 | 17.23 |
| Gajapati | Kankada | Siali | 127105 | 53810 | 42.34 |
|  | Mohona | Chandiput | 119080 | 75065 | 63.04 |
| Ganjam | Kukudak | Sihala | 128265 | 113485 | 88.48 |
|  | Surada | Asurabandha | 119125 | 119125 | 100.00 |
|  | Sheraga | Mahupadar | 470451 | 470451 | 100.00 |
| Jharsuguda | Lakhanp | Panchagaon | 27306 | 17994 | 65.90 |
| Kalahandi | Bhawani | Artal | 269280 | 11900 | 4.42 |
|  | Karlamu | Joradobra | 118161 | 36220 | 30.65 |
| Kandhamal | Phiringia | Luisingi | 391018 | 361511 | 92.45 |
|  | Tikabali | Gulingia | 121392 | 87592 | 72.16 |
| Kendujhar | Kendujh | Raikala | 68503 | 30343 | 44.29 |
|  | Saharap | Malarpada | 203945 | 67991 | 33.34 |
|  | Ghatgaon | Sarasa Pasi | 363045 | 62093 | 17.10 |
| Koraput | Borigum | Pondasguda | 852856 | 182412 | 21.39 |
|  | Nandapu | Khurji | 234800 | 78880 | 33.59 |
|  | Bandhug | Nilabadi | 87645 | 34300 | 39.14 |
| Malkangiri | Malkangi | Gangala | 173750 | 21962 | 12.64 |
|  | Korukonda | Nuaguda | 204854 | 19175 | 9.36 |
| Mayurbhanj | Gopaba | Arapata | 256630 | 256070 | 99.78 |
|  | Badasah | Chandanpur | 146671 | 46385 | 31.63 |
|  | Saraska | Murunia | 103352 | 82399 | 79.73 |
|  | Rasgovi | Debasole | 213230 | 206159 | 96.68 |
| Nabarangpur | Papadah | Papadahandi | 365406 | 96963 | 26.54 |
|  | Chandah | Gambariguda | 221058 | 66735 | 30.19 |
| Nuapada | Sinapali | Ghalamal | 63522 | 26100 | 41.09 |
| Rayagada | Rayagad | Gumma | 120655 | 75380 | 62.48 |
|  | Chandra | Piskapanga | 95600 | 25250 | 26.41 |
| Sambalpur | Kuchind | Hadipali | 288813 | 148881 | 51.55 |
|  | Rairakho | Badbahal | 253575 | 81896 | 32.30 |
|  | Biramahar | Mursundhi | 414268 | 10570 | 2.55 |
| Sundergarh | Kutra | Ambhagova | 126711 | 75691 | 59.74 |
|  | Bonarigar | Sarsara Balang | 55531 | 11567 | 20.83 |
|  | Baragaon | Ekma | 232246 | 136669 | 58.85 |